## 1_Hours_Available
| Kas | Priyanka | Shivani | Rajesh | Rahul | Milestones | % Complt
2018-07-25 | 4 | 4 | 4 | 4 | 4
2018-07-26 | 4 | 4 | 4 | 4 | 4
2018-07-27 | 4 | 4 | 4 | 4 | 4
2018-07-28 | 4 | 4 | 4 | 4 | 4
2018-07-29 | 8 | 8 | 8 | 8 | 8
2018-07-30 | 8 | 8 | 8 | 8 | 8 | Learning and Slides Preparation
2018-07-31 | 4 | 4 | 4 | 4 | 4 | M1 | 20%
2018-08-01 | 4 | 4 | 4 | 4 | 4 |  |  | 1. Shivani: Prepare a usecase and include Data structure of Blockchain into this usecase
2018-08-02 | 4 | 4 | 4 | 4 | 4 |  |  | 2. Priyanka: Prepare a usecase and include classes, interfaces, events, file handling, threads into this use case
2018-08-03 | 4 | 4 | 4 | 4 | 4 |  |  | 3. Rajesh: Prepare tables of 5-7 use cases and insert dummy values in each tables
2018-08-04 | 8 | 8 | 8 | 8 | 8 |  |  | 4. Kaustubh: Prepare a usecase and include smart contract and deploy it on online IDE.
2018-08-05 | 8 | 8 | 8 | 8 | 8 |  |  | 5. Rahul: Prepare and consolidate Architecture diagram, usecase, application work flow.
2018-08-06 | 4 | 4 | 4 | 4 | 4 | Demo Code Related To Each Module
2018-08-07 | 4 | 4 | 4 | 4 | 4 | M2
2018-08-08 | 4 | 4 | 4 | 4 | 4
2018-08-09 | 4 | 4 | 4 | 4 | 4
2018-08-10 | 4 | 4 | 4 | 4 | 4
2018-08-11 | 8 | 8 | 8 | 8 | 8
2018-08-12 | 8 | 8 | 8 | 8 | 8
2018-08-13 | 4 | 4 | 4 | 4 | 4 | Code Document ( Use cae, Sequence Diagram, State Diagram, Architecture, Workflow)
2018-08-14 | 4 | 4 | 4 | 4 | 4 | M3
2018-08-15 | 4 | 4 | 4 | 4 | 4
2018-08-16 | 4 | 4 | 4 | 4 | 4
2018-08-17 | 4 | 4 | 4 | 4 | 4
2018-08-18 | 8 | 8 | 8 | 8 | 8
2018-08-19 | 8 | 8 | 8 | 8 | 8
2018-08-20 | 4 | 4 | 4 | 4 | 4 | Code Document ( Use cae, Sequence Diagram, State Diagram, Architecture, Workflow)
2018-08-21 | 4 | 4 | 4 | 4 | 4 | M4
2018-08-22 | 4 | 4 | 4 | 4 | 4
2018-08-23 | 4 | 4 | 4 | 4 | 4
2018-08-24 | 4 | 4 | 4 | 4 | 4
2018-08-25 | 8 | 8 | 8 | 8 | 8
2018-08-26 | 8 | 8 | 8 | 8 | 8
2018-08-27 | 4 | 4 | 4 | 4 | 4 | Web API Demo
2018-08-28 | 4 | 4 | 4 | 4 | 4 | M5
2018-08-29 | 4 | 4 | 4 | 4 | 4
2018-08-30 | 4 | 4 | 4 | 4 | 4
2018-08-31 | 4 | 4 | 4 | 4 | 4
2018-09-01 | 8 | 8 | 8 | 8 | 8
2018-09-02 | 8 | 8 | 8 | 8 | 8
2018-09-03 | 4 | 4 | 4 | 4 | 4 | Code Document ( Class Digram, SQL Table Diagram, Architecture, Workflow)
2018-09-04 | 4 | 4 | 4 | 4 | 4 | M6
2018-09-05 | 4 | 4 | 4 | 4 | 4
2018-09-06 | 4 | 4 | 4 | 4 | 4
2018-09-07 | 4 | 4 | 4 | 4 | 4
2018-09-08 | 8 | 8 | 8 | 8 | 8
2018-09-09 | 8 | 8 | 8 | 8 | 8
2018-09-10 | 4 | 4 | 4 | 4 | 4
2018-09-11 | 4 | 4 | 4 | 4 | 4
2018-09-12 | 4 | 4 | 4 | 4 | 4 | M7
2018-09-13 | 4 | 4 | 4 | 4 | 4
2018-09-14 | 4 | 4 | 4 | 4 | 4
2018-09-15 | 8 | 8 | 8 | 8 | 8
2018-09-16 | 8 | 8 | 8 | 8 | 8
2018-09-17 | 4 | 4 | 4 | 4 | 4
2018-09-18 | 4 | 4 | 4 | 4 | 4
2018-09-19 | 4 | 4 | 4 | 4 | 4 | M8
2018-09-20 | 4 | 4 | 4 | 4 | 4
2018-09-21 | 4 | 4 | 4 | 4 | 4
2018-09-22 | 8 | 8 | 8 | 8 | 8
2018-09-23 | 8 | 8 | 8 | 8 | 8
2018-09-24 | 4 | 4 | 4 | 4 | 4
2018-09-25 | 4 | 4 | 4 | 4 | 4
2018-09-26 | 4 | 4 | 4 | 4 | 4 | M9
2018-09-27 | 4 | 4 | 4 | 4 | 4
2018-09-28 | 4 | 4 | 4 | 4 | 4
2018-09-29 | 8 | 8 | 8 | 8 | 8
2018-09-30 | 8 | 8 | 8 | 8 | 8
2018-10-01 | 4 | 4 | 4 | 4 | 4
2018-10-02 | 4 | 4 | 4 | 4 | 4
2018-10-03 | 4 | 4 | 4 | 4 | 4 | M10
2018-10-04 | 4 | 4 | 4 | 4 | 4
2018-10-05 | 4 | 4 | 4 | 4 | 4
2018-10-06 | 8 | 8 | 8 | 8 | 8
2018-10-07 | 8 | 8 | 8 | 8 | 8
2018-10-08 | 4 | 4 | 4 | 4 | 4
2018-10-09 | 4 | 4 | 4 | 4 | 4
2018-10-10 | 4 | 4 | 4 | 4 | 4 | M11
2018-10-11 | 4 | 4 | 4 | 4 | 4
2018-10-12 | 4 | 4 | 4 | 4 | 4
2018-10-13 | 8 | 8 | 8 | 8 | 8
2018-10-14 | 8 | 8 | 8 | 8 | 8
2018-10-15 | 4 | 4 | 4 | 4 | 4
2018-10-16 | 4 | 4 | 4 | 4 | 4
2018-10-17 | 4 | 4 | 4 | 4 | 4 | M12
2018-10-18 | 4 | 4 | 4 | 4 | 4
2018-10-19 | 4 | 4 | 4 | 4 | 4
2018-10-20 | 8 | 8 | 8 | 8 | 8
2018-10-21 | 8 | 8 | 8 | 8 | 8
2018-10-22 | 4 | 4 | 4 | 4 | 4
2018-10-23 | 4 | 4 | 4 | 4 | 4
2018-10-24 | 4 | 4 | 4 | 4 | 4 | M13
2018-10-25 | 4 | 4 | 4 | 4 | 4
2018-10-26 | 4 | 4 | 4 | 4 | 4
2018-10-27 | 8 | 8 | 8 | 8 | 8
2018-10-28 | 8 | 8 | 8 | 8 | 8
2018-10-29 | 4 | 4 | 4 | 4 | 4
2018-10-30 | 4 | 4 | 4 | 4 | 4
2018-10-31 | 4 | 4 | 4 | 4 | 4 | M14
2018-11-01 | 4 | 4 | 4 | 4 | 4
2018-11-02 | 4 | 4 | 4 | 4 | 4
2018-11-03 | 8 | 8 | 8 | 8 | 8
2018-11-04 | 8 | 8 | 8 | 8 | 8
2018-11-05 | 4 | 4 | 4 | 4 | 4
2018-11-06 | 4 | 4 | 4 | 4 | 4
2018-11-07 | 4 | 4 | 4 | 4 | 4 | M15
2018-11-08 | 4 | 4 | 4 | 4 | 4
2018-11-09 | 4 | 4 | 4 | 4 | 4
2018-11-10 | 8 | 8 | 8 | 8 | 8
2018-11-11 | 8 | 8 | 8 | 8 | 8
2018-11-12 | 4 | 4 | 4 | 4 | 4
2018-11-13 | 4 | 4 | 4 | 4 | 4
2018-11-14 | 4 | 4 | 4 | 4 | 4 | M16
2018-11-15 | 4 | 4 | 4 | 4 | 4
2018-11-16 | 4 | 4 | 4 | 4 | 4
2018-11-17 | 8 | 8 | 8 | 8 | 8
2018-11-18 | 8 | 8 | 8 | 8 | 8
2018-11-19 | 4 | 4 | 4 | 4 | 4
2018-11-20 | 4 | 4 | 4 | 4 | 4
2018-11-21 | 4 | 4 | 4 | 4 | 4 | M17
2018-11-22 | 4 | 4 | 4 | 4 | 4
2018-11-23 | 4 | 4 | 4 | 4 | 4
2018-11-24 | 8 | 8 | 8 | 8 | 8
2018-11-25 | 8 | 8 | 8 | 8 | 8
2018-11-26 | 4 | 4 | 4 | 4 | 4
2018-11-27 | 4 | 4 | 4 | 4 | 4
2018-11-28 | 4 | 4 | 4 | 4 | 4 | M18
2018-11-29 | 4 | 4 | 4 | 4 | 4
2018-11-30 | 4 | 4 | 4 | 4 | 4
2018-12-01 | 8 | 8 | 8 | 8 | 8
2018-12-02 | 8 | 8 | 8 | 8 | 8
2018-12-03 | 4 | 4 | 4 | 4 | 4
2018-12-04 | 4 | 4 | 4 | 4 | 4
2018-12-05 | 4 | 4 | 4 | 4 | 4 | M19
2018-12-06 | 4 | 4 | 4 | 4 | 4
2018-12-07 | 4 | 4 | 4 | 4 | 4
2018-12-08 | 8 | 8 | 8 | 8 | 8
2018-12-09 | 8 | 8 | 8 | 8 | 8
2018-12-10 | 4 | 4 | 4 | 4 | 4
2018-12-11 | 4 | 4 | 4 | 4 | 4
2018-12-12 | 4 | 4 | 4 | 4 | 4 | M20
2018-12-13 | 4 | 4 | 4 | 4 | 4
2018-12-14 | 4 | 4 | 4 | 4 | 4
2018-12-15 | 8 | 8 | 8 | 8 | 8
2018-12-16 | 8 | 8 | 8 | 8 | 8
2018-12-17 | 4 | 4 | 4 | 4 | 4
2018-12-18 | 4 | 4 | 4 | 4 | 4
2018-12-19 | 4 | 4 | 4 | 4 | 4 | M21
2018-12-20 | 4 | 4 | 4 | 4 | 4
2018-12-21 | 4 | 4 | 4 | 4 | 4
2018-12-22 | 8 | 8 | 8 | 8 | 8
2018-12-23 | 8 | 8 | 8 | 8 | 8
2018-12-24 | 4 | 4 | 4 | 4 | 4
2018-12-25 | 4 | 4 | 4 | 4 | 4
2018-12-26 | 4 | 4 | 4 | 4 | 4 | M22
2018-12-27 | 4 | 4 | 4 | 4 | 4
2018-12-28 | 4 | 4 | 4 | 4 | 4
2018-12-29 | 8 | 8 | 8 | 8 | 8
2018-12-30 | 8 | 8 | 8 | 8 | 8
2018-12-31 | 4 | 4 | 4 | 4 | 4
2019-01-01 | 4 | 4 | 4 | 4 | 4
2019-01-02 | 4 | 4 | 4 | 4 | 4 | M23
2019-01-03 | 4 | 4 | 4 | 4 | 4
2019-01-04 | 4 | 4 | 4 | 4 | 4
2019-01-05 | 8 | 8 | 8 | 8 | 8
2019-01-06 | 8 | 8 | 8 | 8 | 8
2019-01-07 | 4 | 4 | 4 | 4 | 4
2019-01-08 | 4 | 4 | 4 | 4 | 4
2019-01-09 | 4 | 4 | 4 | 4 | 4 | M24
2019-01-10 | 4 | 4 | 4 | 4 | 4
2019-01-11 | 4 | 4 | 4 | 4 | 4
2019-01-12 | 8 | 8 | 8 | 8 | 8
2019-01-13 | 8 | 8 | 8 | 8 | 8
2019-01-14 | 4 | 4 | 4 | 4 | 4
2019-01-15 | 4 | 4 | 4 | 4 | 4
2019-01-16 | 4 | 4 | 4 | 4 | 4 | M25
2019-01-17 | 4 | 4 | 4 | 4 | 4
2019-01-18 | 4 | 4 | 4 | 4 | 4
2019-01-19 | 8 | 8 | 8 | 8 | 8
2019-01-20 | 8 | 8 | 8 | 8 | 8
2019-01-21 | 4 | 4 | 4 | 4 | 4
2019-01-22 | 4 | 4 | 4 | 4 | 4
2019-01-23 | 4 | 4 | 4 | 4 | 4 | M26
2019-01-24 | 4 | 4 | 4 | 4 | 4
2019-01-25 | 4 | 4 | 4 | 4 | 4
2019-01-26 | 8 | 8 | 8 | 8 | 8
2019-01-27 | 8 | 8 | 8 | 8 | 8
2019-01-28 | 4 | 4 | 4 | 4 | 4
2019-01-29 | 4 | 4 | 4 | 4 | 4
2019-01-30 | 4 | 4 | 4 | 4 | 4 | M27 |  | Total Hours | 5640
2019-01-31 | 4 | 4 | 4 | 4 | 4
2019-02-01 | 4 | 4 | 4 | 4 | 4
2019-02-02 | 8 | 8 | 8 | 8 | 8
2019-02-03 | 8 | 8 | 8 | 8 | 8
2019-02-04 | 4 | 4 | 4 | 4 | 4
2019-02-05 | 4 | 4 | 4 | 4 | 4
2019-02-06 | 4 | 4 | 4 | 4 | 4 | M28
2019-02-07 | 4 | 4 | 4 | 4 | 4
2019-02-08 | 4 | 4 | 4 | 4 | 4
2019-02-09 | 8 | 8 | 8 | 8 | 8
2019-02-10 | 8 | 8 | 8 | 8 | 8
2019-02-11 | 4 | 4 | 4 | 4 | 4
2019-02-12 | 4 | 4 | 4 | 4 | 4
2019-02-13 | 4 | 4 | 4 | 4 | 4 | M29
2019-02-14 | 4 | 4 | 4 | 4 | 4
2019-02-15 | 4 | 4 | 4 | 4 | 4
2019-02-16 | 8 | 8 | 8 | 8 | 8
2019-02-17 | 8 | 8 | 8 | 8 | 8
2019-02-18 | 4 | 4 | 4 | 4 | 4
2019-02-19 | 4 | 4 | 4 | 4 | 4
2019-02-20 | 4 | 4 | 4 | 4 | 4 | M30
2019-02-21 | 4 | 4 | 4 | 4 | 4
2019-02-22 | 4 | 4 | 4 | 4 | 4
2019-02-23 | 8 | 8 | 8 | 8 | 8
2019-02-24 | 8 | 8 | 8 | 8 | 8
2019-02-25 | 4 | 4 | 4 | 4 | 4
2019-02-26 | 4 | 4 | 4 | 4 | 4
2019-02-27 | 4 | 4 | 4 | 4 | 4 | M31
2019-02-28 | 4 | 4 | 4 | 4 | 4
2019-03-01 | 4 | 4 | 4 | 4 | 4
| 1128 | 1128 | 1128 | 1128 | 1128

## Learning_Details_M4
KST
R
Ra
Shi
Priya

## Use_Cases_M5
Basic Flow | KA | RK | PR | SH | RA
Login Flow
Registration
Display Details
Book a Medical Practisionor
Generate Privat/Public Key
Confirm Booking
Medical Practisionor' Detail
Assign A Prescription
Validate Presciption
Validate Patient/ Client
Store Public Details in DB
Validate Patient/ Client Using Fingerprint
Validate Medical Practisoner Using Public Key
Document Processing Smart Contract

## Screen_Design_M5
Basic Flow | KA | RK | PR | SH | RA
Login Flow
Registration
Display Details
Book a Medical Practisionor
Generate Privat/Public Key
Confirm Booking
Medical Practisionor' Detail
Assign A Prescription
Validate Presciption
Validate Patient/ Client
Store Public Details in DB
Validate Patient/ Client Using Fingerprint
Validate Medical Practisoner Using Public Key
Document Processing Smart Contract

## Web_Api
Basic Flow | KA | RK | PR | SH | RA
Login Flow
Registration
Display Details
Book a Medical Practisionor
Generate Privat/Public Key
Confirm Booking
Medical Practisionor' Detail
Assign A Prescription
Validate Presciption
Validate Patient/ Client
Store Public Details in DB
Validate Patient/ Client Using Fingerprint
Validate Medical Practisoner Using Public Key
Document Processing Smart Contract

## Sequence_Diagram_M5
Basic Flow | KA | RK | PR | SH | RA
Login Flow
Registration
Display Details
Book a Medical Practisionor
Generate Privat/Public Key
Confirm Booking
Medical Practisionor' Detail
Assign A Prescription
Validate Presciption
Validate Patient/ Client
Store Public Details in DB
Validate Patient/ Client Using Fingerprint
Validate Medical Practisoner Using Public Key
Document Processing Smart Contract

## State_Diagram_M5
Basic Flow | KA | RK | PR | SH | RA
Login Flow
Registration
Display Details
Book a Medical Practisionor
Generate Privat/Public Key
Confirm Booking
Medical Practisionor' Detail
Assign A Prescription
Validate Presciption
Validate Patient/ Client
Store Public Details in DB
Validate Patient/ Client Using Fingerprint
Validate Medical Practisoner Using Public Key
Document Processing Smart Contract